## Caledon Comments
Official Plan Amendment, Zoning By-law Amendment, Site Plan Application and Draft Plan Condominium Application
POPA 2021-0011, RZ 2021-0015, SPA 2021-0077 and 21CDM 21004C
| Comment | Responsibility #1 | Responsibility #2 | Responisbility #3 | Notes | Internal Due Date | Response
Finance
Hussein Visanji, Senior Financial Analyst
| Currently, applicable Development Charge (Residential) rates are as follows: | Camcos |  |  |  |  | This comment is noted. The applicable development charges will be paid.
| Town of Caledon: (a) $41,413.92 per apartment > 70 sq. metres; (b) $24,305.21 per apartment <= 70 sq. metres; and (c) $54,608.35 per townhouse dwelling. Stacked townhouses will attract Development Charges at the large apartment rates. All other townhouses will attract Development Charges at the Residential (Other) rates. These rates are valid to July 31, 2025. | Camcos
| Region of Peel: (a) $54,476.68 per apartment > 70 sq. metres; (b) $28,811.18 per apartment <= 70 sq. metres; and (c) $59,481.10 per townhouse dwelling. These rates are valid to July 31, 2025. | Camcos
| School Boards: (a) $5,076 per any residential unit. Rate is valid to June 30, 2025. | Camcos
| GO Transit: (a) $602.70 per apartment > 70 sq. metres; (b) $312.33 per apartment <= 70 sq. metres; and (c) $843.71 per townhouse dwelling. These rates are valid to July 31, 2025. | Camcos
Fire and Emergency Services
Anthony Staniscia
anthony.staniscia@caledon.ca
1 | The community Risk Assessment indicates a significant gap in the delivery of an appropriate level of fire suppression services within the Bolton Rural Service Centre. Fire Services does not recommend increasing this risk until further strides are made in the fire suppression deployment benchmarks including 10 firefighters responding within a 10 minute response time (turnout time + travel time) to 80% of the fire related incidents within the Bolton Rural Service Centre boundaries. | Q4 |  |  |  |  | This comment is noted.
2 | What is the OBC construction type? It is unclear in the data matrix. | Q4 |  |  |  |  | This comment is noted. Building #1 is non combustible construction. Building 2 & 3 is wood frame combustible construction.
3 | Will Building 1 be registered under the Retirement Homes Act? | Q4 |  |  |  |  | This comment is noted. The project will not be registered under the Retirement Homes Act
4 | Will building 1 have special care provided by the facility, directly through staff or indirectly through another provider to residents? | Q4 |  |  |  |  | The project is not intended to be a care or retirement facility
5 | Explain the Building Area BA of the townhouse buildings, over 600sqm is a part 3 building. The Building Dept will have to be consulted on this matter for interpretation. | Q4 |  |  |  |  | This comment is noted. A Fire Wall whas been added to allow for two separate fire compartments and keep townhouses under Part 9 OBC. - BLDG#2a Area is 400 m2 - BLDG#2b Area is 202 m2 - BLDG#4 Area is 500 m2
6 | Explain the classification of the townhouse building as 3 storey when there are 4 floors. The Building Dept will have to be consulted on this matter for interpretation. | Q4 |  |  |  |  | This comment is noted. As per OBC, these units only have 3 storeys of occupied space. Roof terrace is not considered a storey. It's exterior amenity space
7 | Where are the firefighter entrances to the townhouse units? What is the unobstructed distance for firefighters from the firetruck? Garages with cars parked inside or stored items shall not be considered as entry for firefighters as this would be obstructing access. | Q4 |  |  |  |  | Refer to sheet SPA003 - dimensions have been provided to identify distance from access road to the main entrance of the townhouses. Garages have not been considered entrances/exits for firefighting purposes.
8 | Hydrants and fire flow must be satisfactory to the Region of Peel. | Q4 |  |  |  |  | This comment is noted.
Town Legal
Michelle Halsall
anthony.staniscia@caledon.ca
| Legal Description: PIN: 14326-1856 (LT) – Firstly: Part of Lot 9, Concession 5 (Albion), designated as Part 2 on 43R-10166; Save and except Part 11 on 43R-30691; Subject-to an easement in gross over Part 12 on 43R-30591 as in PR1070814; Subject-to an easement for entry as in PR1191573; Secondly: Part of Lot 9, Concession 5 (Albion), designated as Part 1 on 43R-28725; Save and except Part 10 on 43R-30591; Subject to an easement for entry as in PR1191573; Town of Caledon; Regional Municipality of Peel. | [5 empty] | This condition is noted.
Name(s) of Registered Owner(s): Camcos (Bolton Village) Inc.
Mortgage(s): Instrument PR4208490, is a mortgage registered on June 7, 2023, in favour of Cameron Stephens Mortgage Capital Ltd. If a Site Plan Agreement will be entered into, postponements of this mortgage to the Site Plan Agreement will be required prior to registration of the agreement.
Easement(s) with the Town or Region: None.
Other Issues:
1 | Please note that Legal Services is no longer commenting on zoning by-law amendments or draft official plan amendments.
2 | As noted in my email with correspondence with Muhammad, Legal Services cannot comment or provide draft conditions until we are in receipt of the draft plan of condominium for review.
Municipal Number
Emily King
Emily.King@caledon.ca
| The current property address is confirmed as 13656 &13668 Emil Kolb Parkway | [5 empty] | This comment is noted.
| Should the application be approved a new municipal number shall be issued in accordance with the Municipal Numbering By-law and Guidelines. This number will be issued in accordance with these documents, based on an approved driveway location. | Camcos
| A municipal number will be issued at the earliest of grading approval, servicing approval or Final Site Plan Approval. | Camcos
| Upon issuance of one of the above-noted approvals, the Lead Planner will forward a copy of the approval package to municipal numbering staff to work with the owner to issue the required number and post any required signage of the number in accordance with the Town’s Municipal Numbering By-law and Guidelines. | Camcos
| In accordance the Municipal Numbering By-law and Guidelines, the municipal number must be posted on the exterior of the building that faces the road on which the building is numbered. The elevation drawings shall identify the location of the municipal address on the elevations and those drawings shall form part of the approval package. The number shall be identified in accordance with the By-law and Guidelines. Should the owner require clarification on the requirements of the By-law, please contact municipal numbering staff at municipalnumbers@caledon.ca or 905-584-2272 x. 7338. | Camcos
| The information provided is satisfactory to issue a Municipal Number | Camcos
Parks
Halley Patel
Halley.patel@caledon.ca
| Payment of money in lieu of conveyance of parkland will be required, according to the sections 9 (b) and 17 (b) of the Town’s Parkland Dedication By-law -2022-042, prior to issuance of any building permits. | Camcos |  |  |  |  | This condition is noted. Cash in Lieu payment and corresponding appraisal will be provided.
| Cash-in-lieu of parkland is required at equivalent market value of 5% of the total land area. To determine the current market value of the development land, the Owner will be required to obtain and furnish the Town with an concise narrative appraisal, in accordance with the Town of Caledon’s Parkland Conveyance By-law - 2022-042. Appraisal is considered valid for a maximum period of six months. | Camcos
| The appraisal needs to be prepared by a certified professional appraiser of real estate who is designated as an Accredited Appraiser by the Appraisal Institute of Canada (AIC), and who is a member in good standing of the AIC, at no expense to the Town. All appraisals must comply with the current Canadian Uniform Standards of Professional Appraisal Practice (CUSPAP) as adopted by the Appraisal Institute of Canada. | Camcos
Urban Design - POPA 2021-0011, RZ 2021-0015
1 | Townhouse block should be no more than 8 units. | Q4 | Camcos |  | Confirm regulation |  | This condition is noted. Zoning Standard RT allows for 12units . The development proposes two blocks, one of 12 units and the other with 10 units.
2 | A Sun Shadow Study is required for any building over 5 storeys in height. As noted in the Town’s Terms of Reference for the Study, please include additional written descriptions of the impacts and findings of the study. | Q4 |  |  | Confirm is sun shadow is being provided |  | This comment is noted. A shadow study has been provided with the original application, please refer to sheets SPA600 & SPA601
3 | An Urban Design Brief was requested as a complete application requirement. Within the UDB please include details on: | Q4 |  |  | Urban Design Brief |  | This comment is noted. An Urban Design Brief has been incldued within this submission.
a) | Site layout reasoning and justification. Please explore having the mid-rise building fronting onto Emil Kolb pkwy. Since Emil Kolb is the higher capacity road the proposed height and density would be more appropriate fronting onto this street. | Q4 |  |  |  |  | This comment is noted. The proposed building has been positioned at the corner of the site to provide appropriate separation from the lower-density housing on the neighbouring lots. This configuration establishes a gradual transition in scale, supporting the residential character of the surrounding area. The north elevation of the mid-rise building, oriented toward the townhouses, has been proportionally and intentionally stepped back to reduce perceived height impacts on adjacent buildings. The siting of the townhouses also responds to privacy considerations, with their design ensuring a sensitive and compatible interface with neighbouring properties. In addition, the site layout accommodates an efficient circulation system, allowing the entrance, waste collection, and fire route to operate within a continuous loop.
i) | If this layout provides constraints, consider an L shaped building that steps down into the townhouses that front onto Harvestmoon dr. | Q4 |  |  |  |  | This comment is noted. Preliminary feasibility studies showed that an L shape building limits the continuity of services throughout the site. It is also less efficient and it makes some of the units less marketable, while limiting more the number of parking spaces allocated on the site.
4 | The elevations show unique step-backs and massing changes on the north and west elevations. These changes would be more appropriate on the south and east elevations as they are the street facing facades and would enhance the pedestrian streetscape experience. We recommend mirroring the building along the east-west axis. | Q4 |  |  |  |  | This comment is noted. A review of the elevations has been completed and there are materials and massing changes on the South and East elevations which enhance the building's scale and presence onto the street and neighbouring areas.
a) | Balcony insets and projections will need to be adjusted for this proposed change | Q4
5 | We would encourage a greater setback at the corner of Emil Kolb and Harvestmoon to provide for a civic space and accentuate the public entry. | Q4 |  |  |  |  | This comment is noted. The proposed redesign of the building and site allows for a more active corner. Extensive sidewalks and pedestrian areas promote walkability and interactions at the corner of the site, and the main entrance to the building is located here, providing enhanced connectivity to the public realm.
6 | Setback Townhouse balconies at least 10 metres from the rear property line to minimize overlook. | Q4 |  |  |  |  | This comment is noted. Townhouses’ terraces facing the rear property line are currently screened by proposed vegetation that provide privacy and separation of properties. Additional landscaping can be added to the terraces in the form of planters to provide further privacy to neighbouring houses.
a) | Provide landscape elements to assist in buffering the balconies from the adjacent low-rise residential | Q4 | Landscape Planning
Urban Design - SPA 2021-0077, 21CDM-21004C
Accessibility
1 | Exterior paths of travel, including outdoor sidewalks and walkways, shall have a minimum clear width of 1.5 metres, a surface which is firm, stable and slip resistant and otherwise comply with the Integrated Accessibility Standards (IAS) within the Accessibility for Ontarians with Disabilities Act (AODA). | Q4 | Landscape Planning |  |  | 2025-10-27 | This comment is noted. All pathways are 1.5m wide and constructed from a hard/slip-resistent material (concrete or asphalt) in accordance with AODA.
2 | Where a curb ramp connects with an exterior path of travel (walkway or sidewalk), a minimum clear width of 1.2 metres shall be provided beyond the curb ramp to serve as a turning space. Please dimension. | Q4 |  |  |  | 2025-10-27 | This comment is noted and addressed.
3 | As per the IAS within the AODA, provide the required percentage of accessible parking spaces based on the total number of parking spaces calculated for the development, rounding up to the nearest whole number, for the use of persons with disabilities. a. 174*4%= 7 spaces | Q4 |  |  |  | 2025-10-27 | This comment is noted and addressed.
4 | An accessible aisle that directly leads to an access route or walkway shall contain a curb ramp that meets the provisions of the Ontario Building Code as it relates to curb ramps. | Q4 |  |  |  | 2025-10-27 | This comment is noted and addressed.
5 | The accessible parking spaces shall each be identified with an accessible parking sign which shall be depicted on the Site Plan to confirm compliance with the Integrated Accessibility Standards (IAS). | Q4 |  |  |  | 2025-10-27 | This comment is noted and addressed.
6 | Site Plan shall indicate that the main entrance shall be fully accessible to persons with a disability by inclusion of a power door operator or automatic sliding door. | Q4 |  |  |  | 2025-10-27 | This comment is noted and addressed.
7 | Snow storage area shall not be adjacent to accessible parking spaces nor piled within the space. Site Plan shall depict the location of the snow storage on the property for confirmation. | Q4 |  |  |  | 2025-10-27 | This comment is noted and addressed.
Urban Design
1 | Please review sections 6, 9.3.2, 9.3.7, 9.4, 9.6, 9.7, & 9.8 in the updated Town Wide Design Guidelines. | ALL |  |  |  |  | This comment is noted.
2 | An Urban Design Brief was requested as a complete application requirement. Within the UDB please include details on: the proposed garbage privacy screen, the retaining wall design, sustainability initiatives, proposed materiality, CPTED design choices, proposed pedestrian and streetscape design, and townhouse utility locations. | Q4 |  |  |  | 2025-10-27 | This comment is noted. An Urban Design Brief has been incldued within this submission.
a) | Please also include a cross section graphic through Harvestmoon to the building to better understand the proposed streetscape character | Q4 |  |  |  | 2025-10-27 | This comment is noted and addressed. Please refer to drawing SPA602.
3 | Please ensure that any inset balconies will still receive appropriate sunlight. | Q4 |  |  |  | 2025-10-27 | This condition is noted.
4 | As there is no proposed outdoor amenity space for the site, we would recommend exploring a linear park through the parking area. This addition would also assist with breaking up the visual of a large parking lot from Emil Kolb. | Q4 | Camcos |  |  | 2025-10-27 | This comment is noted.Revised Site Plan proposes planters along parking spaces to screen and fragment paved areas, larger landscaping areas and decorative pavers to enhance pedestrian pathways traversing the parking area. An amenity area is proposed within the surplus land east of the site to provide sitting areas for the residents of the site and surroundings, while screening the parking areas from the street.
a) | Please include required parking numbers within the Site Statistics table | Q4 |  |  |  | 2025-10-27 | This comment is noted. This item has been addressed. Please refer to drawing SPA001.
5 | Please include crosswalks leading to the apartment building main entrance. | Q4 |  |  |  | 2025-10-27 | This comment is noted. This item has been addressed. Please refer to drawing SPA001.
6 | As indicated in the Town of Caledon Site Plan Control Manual, elevations must show lighting, air and exhaust vents, and any roof top mechanical equipment. | Q4 |  |  |  | 2025-10-27 | This comment is noted. There is no lighting on the building. The air and exhaust vents will be added at design development stage.
7 | Accentuate all public entries by integrating intuitive signage, effective architectural features (for example, canopies, change in building massing), and hard and soft landscaping elements. | Q4 |  |  |  | 2025-10-27 | This comment is noted.
8 | The east ground floor elevation provides very little glazing and activation to the street, please consider if there are ground floor layout changes that can be made to provide more windows along the east façade. Corner buildings must have facades that address both street frontages. | Q4 |  |  |  | 2025-10-27 | This comment is noted. Glazing has been added where applicable. The corner of the building houses the waste and recycling room, therefore glazing is limited.
9 | We would encourage the step-backed inaccessible roof areas to be used as green roofs. | Q4 |  |  |  | 2025-10-27 | This comment is noted.
10 | We recommend combining the step-backs with changes in façade materials and textures. | Q4 |  |  |  | 2025-10-27 | This condition is noted. Please refer to SPA200, SPA201 & SPA202 for elevation changes.
11 | The ground floor parking should have additional screening beyond the proposed low vegetation. | Q4 |  |  |  | 2025-10-27 | This comment is noted. Vegetation will be used for screening of the parking under the building. Please refer to Landscaping drawings for details.
12 | The end unit of the townhouse block adjacent to Emil Kolb shall have priority lot features. | Q4 |  |  |  | 2025-10-27 | This comment is noted.
Zoning
David Shortt
POPA 2021-0011 Zoning Comments:
| Zoning staff have no comments with regards to POPA 2021-0011. | [5 empty] | This comment is noted.
21CDM-21004C Zoning Comments:
| Zoning notes that no drawings have been submitted for this application. Drawings and related documents to be submitted once OPA, ZBA and SPA have been approved. | [5 empty] | This comment is noted.
RZ 2021-0015 Zoning Comments:
1 | Zoning notes that the Draft By-law indicates a minimum Dwelling Unit Area of 67m2; however, certain dwelling units within Building 1 appear to be less than 67m2, which does not comply. Consider revising the Draft By-law to ensure consistency. Please see Draft By-law comments for more information. | Q4 | Humphries |  |  | 2025-10-27 | This comment is noted.The smallest unit in Building 1 is 47m2. The revision is reflected in the updated Draft By Law.
2 | Zoning notes that Building Area has been identified on the submitted Site Plan as 23.6%, whereas the Draft By-law indicates a maximum of 23.5%. Please revise accordingly. | Q4 | Humphries |  |  | 2025-10-27 | This comment is noted and updated within the Draft By Law.
3 | Zoning notes that the parent Multiple Residential (RM) Zone requires a minimum parking space setback of 6.0 metres from any street line. The submitted site plan appears to show parking spaces for the Building, Apartment at 5.0 metres from the street line and parking spaces for the Dwelling, Stacked Back-to-Back Townhouse at 3.50 metres from the street line. Please revise accordingly or propose relief from this provision in the Draft By-law. | Q4 | Humphries |  |  | 2025-10-27
4 | Applicant to demonstrate compliance with Privacy Yard and Play Facility requirements as per the parent Multiple Residential (RM) Zone. | Q4 |  |  |  | 2025-10-27
5 | Zoning notes that the parent Multiple Residential (RM) Zone requires a minimum Landscaping Area of 45%. The submitted site plan appears to show a Landscaping Area of 20.69%. Please revise accordingly or propose relief from this provision in the Draft By-law. | Q4 | Humphries | Landscape Planning |  | 2025-10-27 | This comment is noted. Landscaped area has increased to 24%. Please refer to the updated Draft By Law.
6 | Zoning notes that the parent Multiple Residential (RM) Zone requires a minimum of 1 play facility area for each lot with more than 10 dwelling units. The submitted site plan and floor plans do not appear to show a play facility area. Zoning requests the applicant please revise or propose relief from this provision on the Draft By-law. Please note that as per the RM Zone, play facility areas shall only be permitted in a rear yard or interior side yard but not in any portion of a privacy yard. | Q4 | Humphries | Landscape Planning |  | 2025-10-27 | This comment is noted. A play facility is proposed on the surplus land East of the Easterly property line. A childrens play area/seating/shade structure has been shown on the landscape drawings.
a) | A Play Facility Area is defined as, “Play Facility Area means that portion of a lot dedicated to children's outdoor equipment and associated play area.” | Q4 | Humphries | Landscape Planning |  | 2025-10-27
7 | Applicant to confirm maximum lighting fixture heights and setbacks in accordance with Section 5.2.18 “Illumination” of Town of Caledon Zoning By-law 2006-50, as amended. Be advised that Section 5.2.18 “Illumination” permits a minimum setback of 4.5 metres for a lighting fixture from any lot line and a maximum height of 9.0 metres from grade. | Q4 |  |  |  | 2025-10-27 | This comment is noted. Please reference updated Electrical Plans.
8 | Applicant to confirm Schedule “A” has been provided in accordance with the Town of Caledon digital submission standards. | TBC |  |  |  | 2025-10-27 | This comment is noted.
9 | Applicant to ensure that the legal descriptions for both properties are properly captured in Paragraph 2 of the Draft By-law. | Humphries |  |  |  | 2025-10-27 | This comment is noted and updated within the Draft By Law.
10 | Zoning staff have added a definition to the Draft By-law to identify the Front Lot Line as Harvest Moon Drive in order to maintain clarity and consistency. | Humphries |  |  |  | 2025-10-27 | This comment is noted. Landscaped area has increased to 24%. Please refer to the updated Draft By Law.
11 | Please see the draft by-law comments provided. Any future copies of the draft by-law must be in Microsoft Word format (no PDF to Word conversions). Tracked changes are recommended but not required. | Humphries |  |  |  | 2025-10-27 | This comment is noted.
SPA 2021-0077 Zoning Comments:
1 | Zoning notes that the following Site Plan Application comments are preliminary and are subject to change pending any revisions or approval to the proposed Zoning By-law Amendment. | [5 empty] | This condition is noted.
2 | Zoning notes that the proposed Draft By-law indicates a minimum Dwelling Unit Area of 67m2. Several Dwelling Units within Building 1 appear to be less than 67m2. Please revise accordingly. | Q4 | Humphries |  |  |  | This comment is noted. Please refer to the updated Draft By Law.
3 | Zoning notes that Building Area has been identified on the submitted site plan as 23.6%, whereas the Draft By-law requires a minimum Building Area of 23.5%. Please revise accordingly. | Q4 | Humphries |  |  |  | This comment is noted. Please refer to the updated Draft By Law.
4 | Zoning notes that the minimum exterior side yard abutting Building 1 appears to be 0.10 metres, whereas the Draft By-law permits a minimum exterior side yard of 2.5 metres. Please revise accordingly. | Q4 | Humphries |  |  |  | This item may have to be addressed in the Draft by-law to note the exterior side yard as a zero-lot line setback, possibly requiring a minor variance. Setting the building back at the corner to meet the minimum 2.5m will affect the unit count and number of parking spaces available greatly.
5 | Zoning notes that Finished Grade, as defined below, has not been properly identified on the submitted Elevation Drawings. Applicant to provide finished grade in order to determine building height compliance. | Q4 | Humphries |  |  |  | This comment is noted and addresssed. Please refer to SPA200, SPA201 & SPA202.
a) | Finished Grade means the average surface elevation at the outside walls of any building or structure, which is determined by taking the arithmetic mean of the levels of the finished ground surface at every location of change of grade at the outside walls of the building or structure. | Q4 | Humphries |  |  |  | This comment is noted.
6 | Zoning notes that a Landscaping Area of 20.69% has been provided, whereas the By-law permits a minimum Landscaping Area of 45% in the RM Zone. Revisions or relief from the By-law is required. | Q4 | Humphries |  |  |  | This comment is noted. Proposed Site plan increases the landscaping areas to 24%. Relief is requested within the Zoning By-law ammendment. Proposed shaded sitting area could provide 346m2 more of landscaping areas for a total of 28% overall, although this is external to the site.
7 | Zoning requests the applicant please demonstrate compliance with the Privacy Yard and Play Facility provisions of the parent RM Zone. | Q4 | Humphries |  |  |  | This comment is noted. Please refer to the updated Draft By Law.
8 | Zoning notes that a parking space setback of 3.5 metres to a street line has been provided, whereas the By-law permits a minimum parking space setback of 6.0 metres in the RM Zone. Revision or relief from the By-law is required. | Q4 | Humphries |  |  |  | This comment is noted. Please refer to the updated Draft By Law.
9 | Zoning notes that a total of two (2) barrier-free parking spaces have been provided, whereas the By-law requires a minimum of seven (7) barrier-free parking spaces for such lot. Revision or relief from the By-law is required. | Q4 |  |  |  |  | This condition is noted. The updated site plan accomodates 7 barrier free parking spots.
10 | Zoning requests the applicant please provide the proposed height of all lighting fixtures in accordance with Section 5.2.18 “Illumination” of Town of Caledon Zoning By-law 2006-50, as amended. Zoning notes that the proposed lighting fixtures appear to be setback 1.3 metres from the interior side lot line, whereas the By-law permits a minimum setback of 4.5 metres for a lighting fixture from any lot line. Be advised that a lighting fixture shall have a maximum height of 9.0 metres above grade and a minimum setback of 4.5 metres from any lot line. | RTG | Q4 |  | Confirm with Ted |  | This comment is noted. The fixtures are proposed within the site facing out and are all setback more than 4.5m from the property line.The proposed poles are 6.0m poles mounted to a decorative base that is 1.0m above grade so the fixtures will be at 7.0m above grade.
Heritage
Sally Drummond
Archaeological Resources
1 | The Town is in receipt of a Stage 1 & 2 Archaeological Assessment of the subject property. No archaeological resources were identified, and staff concur with the report recommendation that the property be considered free of further archaeological concern. | [5 empty] | This comment is noted.
2 | The Town is in receipt of a letter from the Ministry of Heritage, Sport, Tourism and Culture Industries (MHSTCI) advising that the Stage 1& 2 Archaeological Assessment Report for the subject property has been entered into the Public Register without technical review. | [5 empty] | This comment is noted.
3 | There are no further heritage concerns with this application. | [5 empty] | This comment is noted.
Heritage Draft Conditions
1 | The proponent shall immediately stop all work on the Subject Lands and notify the Town’s Heritage staff, Director of Planning, and the Ministry of Heritage, Sport, Tourism and Culture Industries (MHSTCI) in the event that deeply buried archaeological resources are found during the course of any grading or related works on the Subject Lands. Any and all work related to the discovery of deeply buried archaeological resources shall be carried out by the proponent, at their expense, to the satisfaction of the MHSTCI and the Town’s Heritage staff. | [5 empty] | This comment is noted.
Transportation
Kavleen S Younan
1 | Please include the Town's responses to the Terms of Reference (ToR) in the appendix of the report for transparency and future reference. | NexTrans |  |  |  | TIS DRAFT PROVIDED | This comment is noted. The Town's responses are enclosed in Appendix B of the TIS Addendum.
2 | It is noted that a 2% growth rate is being used in the analysis. Please confirm how this rate compares to the growth projections presented in the Environmental Assessment (EA) for the area. | NexTrans |  |  |  | TIS DRAFT PROVIDED | This comment is noted. Given that the growth rates used in the EA report projected higher growth for the southbound and westbound links, the future background traffic volumes were updated accordingly as a conservative approach.
3 | Typically, the use of Synchro for roundabout analysis is not acceptable. Please consult with Regional staff (as the study intersection is under the Region's jurisdiction) to confirm and utilize appropriate software such as ARCADY or RODEL for the roundabout operational analysis. | NexTrans |  |  |  | TIS DRAFT PROVIDED | This comment is noted. It is to be noted that Peel Region’s TIS Guidelines do not explicitly require the use of ARCADY or RODEL software for roundabout operational analysis. While it is noted that both ARCADY and RODEL provide a more conservative analysis of the traffic operations of a roundabout, the Region has not issued any comments regarding out methodology.
4 | Traffic Zone 3153 has been used to determine the traffic distribution. Please include a figure showing the location of this zone relative to the proposed site. Further explanation is required to justify why the traffic distribution from this zone is applicable to the site. | NexTrans |  |  |  | TIS DRAFT PROVIDED | This comment is noted. In accordance with TTS 2006 TAZ, zone 3153 corresponds with the area that the subject site is located and as such, is the most applicable for the assessment of existing traffic distributional patterns.
5 | Please provide a traffic distribution figure indicating the percentage of site-generated traffic assigned to each roadway segment in the study area. | NexTrans |  |  |  | TIS DRAFT PROVIDED | This comment is noted. A traffic distribution figure with percentages is provided in the TIS Addendum.
6 | The current TDM section outlines general measures rather than specific strategies proposed for the subject site. Please revise this section to detail the precise TDM measures being implemented on-site. | NexTrans |  |  |  | TIS DRAFT PROVIDED | This comment is noted. Given the conceptual nature of the development plan, TDM measures will be finalized in subsequent detailed submissions in partnership with the Town to determine what TDM measures will be effective and appropriate for the site.
7 | For all Level of Service (LoS) tables, please include: | NexTrans |  |  |  | TIS DRAFT PROVIDED | This comment is noted.
| Available storage lengths for all turning lanes. | NexTrans |  |  |  | TIS DRAFT PROVIDED | This comment is noted.
| Link distances (distance from the intersection to the nearest access/roadway) for through lanes. | NexTrans |  |  |  | TIS DRAFT PROVIDED | This comment is noted.
| If the Synchro analysis indicates that 95th percentile queues under existing or future background conditions extend beyond the site limits, please conduct a SimTraffic assessment to verify queuing impacts. If queuing issues persist, appropriate mitigation measures must be proposed for the Town’s review. | NexTrans |  |  |  | TIS DRAFT PROVIDED | This comment is noted.
8 | All site accesses must be designed in accordance with OPSD 350.010. For apartment uses, the curb return radii should range between 4.5 to 12.0 metres. | Q4 | NexTrans |  |  | TIS DRAFT PROVIDED | This comment is noted.
9 | A detailed Pavement Markings and Signage Plan is required and must include the following: | NexTrans |  |  |  | TIS DRAFT PROVIDED | This comment is noted. The Pavement Marking and Signage Plan is enclosed in Appendix E of the TIS Addendum.
| All traffic signage to comply with the Ontario Traffic Manual and be installed on streetlight poles where possible. | NexTrans |  |  |  | TIS DRAFT PROVIDED
| The plan must clearly show: | NexTrans |  |  |  | TIS DRAFT PROVIDED
| Roadways | NexTrans |  |  |  | TIS DRAFT PROVIDED
| Property lines | NexTrans |  |  |  | TIS DRAFT PROVIDED
| Driveways | NexTrans |  |  |  | TIS DRAFT PROVIDED
| Fire hydrants | NexTrans |  |  |  | TIS DRAFT PROVIDED
| Sidewalks | NexTrans |  |  |  | TIS DRAFT PROVIDED
| Street lighting | NexTrans |  |  |  | TIS DRAFT PROVIDED
| Traffic signage (regulatory, warning, information) | NexTrans |  |  |  | TIS DRAFT PROVIDED
| Street trees | NexTrans |  |  |  | TIS DRAFT PROVIDED
| Tactile surfaces | NexTrans |  |  |  | TIS DRAFT PROVIDED
| Pavement markings | NexTrans |  |  |  | TIS DRAFT PROVIDED
| All signage must align with: | NexTrans |  |  |  | TIS DRAFT PROVIDED
| The Town’s Traffic By-Law | NexTrans |  |  |  | TIS DRAFT PROVIDED
| Accessibility for Ontarians with Disabilities Act (AODA) | NexTrans |  |  |  | TIS DRAFT PROVIDED
| Highway Traffic Act (HTA) | NexTrans |  |  |  | TIS DRAFT PROVIDED
| Refer to the Town’s Traffic By-Law Schedule P for fire route signage and HTA for accessible parking signage requirements. | NexTrans |  |  |  | TIS DRAFT PROVIDED
| Please include a note on the Site Plan stating that all pavement markings and signage must be installed in accordance with the approved Pavement Markings and Signage Plan to assist Town staff during site inspections. | Q4 |  |  |  | 2025-10-29
10 | Please revise the parking requirements to reflect the correct rates as provided by the Zoning Department. |  |  |  |  | 2025-10-29 | This comment is noted. The plan now reflectes 7 barrier free spaces.
| The only identified deficiency is in Barrier-Free Parking, where 7 spaces are required and only 2 are proposed. | Q4 | NexTrans |  |  | 2025-10-29
| The Town’s preference is that this deficiency be addressed so that the minimum requirement is met. Barrier-free accessible spaces should be designed according to the requirements contained within Schedule O of the Town's Traffic By-Law 2024-048 | Q4 | NexTrans |  |  | 2025-10-29
11 | A detailed review of the access geometry related to OTM/TAC guidelines should be included. The review should include but not be limited to: sight distances; roadway curves (vertical and horizontal) standards; clear zones; conflicting vehicle movements within and adjacent to the development; and on-site vehicle swept path analysis (AutoTurn) utilizing the proper design vehicles (buses, fire trucks, garbage trucks, snowplows, etc., as appropriate). | NexTrans |  |  |  | TIS DRAFT PROVIDED | This condition is noted. A review is provided within the TIS Addendum prepared by NexTrans.
12 | Town requires that the study be stamped, signed, and dated by a licensed Professional Transportation Engineer in Ontario (P.Eng). | NexTrans |  |  |  | TIS DRAFT PROVIDED | This comment is noted.
13 | The Traffic Consultant is requested to submit an updated Transportation Study and a detailed response letter as part of the re-submission package. This letter must clearly reiterate the Town’s comments in order, outlining how each comment has been addressed. | NexTrans |  |  |  | TIS DRAFT PROVIDED | This comment is noted.
Policy Planning
Shahzad Mir
Shahzad.Mir@caledon.ca
Region of Peel Official Plan
| As per the Region of Peel Official Plan, the subject lands are within the Built-Up Area as shown on Schedule E-3 (Growth Plan Policy Areas) and the Urban System as shown on Schedules E-2 (Strategic Growth Areas) and E-1 (Regional Structure). The policies of Chapter 5.6 – Urban System of the Region of Peel Official Plan apply, where applicable. | noted |  |  |  |  | This comment is noted.
Town of Caledon Official Plan (1978)
| The subject lands are within the West Bolton Secondary Plan of the Caledon Official Plan and designated Local Commercial (Section 7.4.6). | noted |  |  |  |  | This comment is noted.
Draft Bolton Secondary Plan
| The draft Bolton Secondary Plan designates the subject property Neighbourhood Areas, with a site-specific policy for commercial policies from the in-force Caledon Official Plan (1978). | noted |  |  |  |  | This comment is noted.
| The draft Bolton Secondary Plan contains a site-specific policy that states buildings should generally not exceed 3-storeys in height within Neighbourhood Areas unless located on the edges of Neighbourhood Areas along an Arterial or Collector Road, where a maximum height of 4-storeys will be permitted. (Section 33.4.b.i). The subject property is located along an arterial road. | noted |  |  |  |  | This comment is noted.
Future Caledon Official Plan
| The permitted uses in the Neighbourhood Areas designation include residential uses; long term care homes and retirement homes, public services facilities that are integral to a neighbourhood; and neighbourhood-scale retail, commercial, personal service and professional service uses that are integrated within mixed-use buildings or on mixed-use sites (Future Caledon section 22.7.2). | Q4 |  |  |  |  | This comment is noted.
| Buildings in low-rise areas will generally not exceed three storeys in height. However, buildings as high as six storeys may be permitted on mixed-use sites (Future Caledon 22.7.3.e). | disregard |  |  |  |  | This comment is noted.
| A six-storeys building may be permitted on the subject lands in accordance with section 22.7.3.e. | disregard |  |  |  |  | This comment is noted.
Engineering
Daniel Oh
Functional Servicing Report and Stormwater Management Report
| To prevent sediment and debris from entering the infiltration facilities—which could lead to clogging and system failure—it is recommended that a pre-treatment measure be implemented upstream of the Cultec system. This will help extend the longevity of the infiltration bed beneath the chambers. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, however please note, due to high ground water levels, infiltration under the Cultec system is not possible.
| Section 2.2 - Design Criteria, states that the Water Balance target for the subject site is 5 mm. This is incorrect. In accordance with the Town’s CLI-ECA guideline, all developments must conduct a water balance assessment to identify the infiltration deficit and implement appropriate LID measures to compensate. Please refer to the Town’s Green Development Standard Guidebook for further guidance. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted. Please refer to the updated Water Balance Section within the FSS.
| The report states that “the groundwater conditions and proposed infiltration facility are being reviewed by the hydrogeologist.” According to the Hydraulic Assessment, the estimated hydraulic conductivity of the native soils ranges from 1 x 10⁻⁹ to 1 x 10⁻⁷ m/s, indicating low permeability. The next submission should evaluate and propose a suitable LID feature compatible with these soil conditions. | Schaeffers | HCS |  |  | Servicing Plans by October 29, 2025 | This comment is noted. Please note the TRCA SWM Criteria makes reference to infiltation facilities up to 10-8 m/s, and a subdrain is included to relieve the infiltration area.
| Drawing 3 of the Hydrogeological Assessment for 13656 Emil Kolb Parkway indicates that perched groundwater elevations are rising northward above 250.5 m. As the stone base elevation of the Cultec system is 256.04 m, please confirm that there will be a minimum clearance of 1.0 m above the seasonally high groundwater table. | HCS |  |  |  |  | This condition is noted. An updated groundwater monitoring summary report provides updated WLs for reference.
| Section 5 of the FRS estimates a construction dewatering rate of 68,100 L/day. This value is based on outdated site information and must be revised in accordance with the current site plan. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted. Please refer to updated FSSR, with updated information from the hydrogeologist.
| The external drainage area shown in Schedule A does not match that shown in Figure 2.1. Please revise for consistency. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted.Refer to updated external drainage area highlighted in Appendix A of the FSSR.
| The storm design chart is missing from the FSR. While the engineering response memo acknowledges the condition of the existing sewer, it does not provide supporting calculations. Please include the required documentation and calculations to verify the sewer’s condition and its capacity to accommodate the proposed stormwater flows. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment Is noted. Please refer to Appendix B for the storm design sheets. Regarding the existing site outlet pipe, as discussed with Town staff, and confirmed by the Town via email (dated August 5, 2025), flows shall not exceed pre-development flows.
General Comments
| The Jellyfish OGS typically requires approximately 0.45m of head to push the water through their filters. The proposed outlet invert elevation of the Jellyfish unit is 255.16 m, while the outlet invert of the diversion manhole (MH2) is 255.32 m, resulting in a driving head of only 0.16 m. Please review the design to ensure sufficient head is provided for proper operation. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted.The jellyfish filter for the subject property is configured in an offline configuration. In an offline configuration, the hydraulic head is calculated from the weir wall elevation (255.62) in MH 2 to the outlet of the Jellyfish Filter unit (255.16) which provides a head of 0.46. Refer to drawing SEC-1.
| Infiltration trenches must be located a minimum of 1.0 m away from structures such as trees and fences, and at least 4.0 m away from buildings. Please relocate the infiltration trenches on the north side of Buildings 2 and 3 to comply with these setback requirements. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted and addressed on drawing SS-1.
| Town staff recognizes that the access to the subject site is temporary and will be impacted by the Emil Kolb Parkway roundabout construction. However, for safety reasons, the access must be designed with appropriate radii. Please refer to Town Transportation’s comments on the required radii specifications | Q4 |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted.
| The existing wood privacy fences along the western and northern property boundaries are not shown on the drawings. According to Drawing SG-1, an additional row of privacy fences is proposed adjacent to the existing ones. Please confirm the existing and proposed fence locations and show them on the drawings. | Q4 | Landscape Planning | Schaeffers |  |  | This comment is noted. Please refer to SPA001 for privacy fence location.
| The Key Plan still shows the site boundary from the previous submission and is incorrect. Please revise. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to updated Key Plan.
| Show the invert of 375mm high-flow bypass and the stone bed elevation of the Cultec system on DWG SEC-1. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted. Refer to the text cross-section 5-5 on drawing SEC-1.
| Show Town’s Wood Screen Fence Detail (STD 605) on Details DWGs. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted. Refer to the updated Details drawings.
| The grass swale running eastward along the north side of Buildings 2 and 3 is poorly defined. Near the northeast corner of Building 3, the swale elevation is higher than the boundary grade which suggests that overland flow will spill onto the boulevard rather than traveling southward to CBMH11. Please revise the design to ensure that site storm drainage remains self-contained. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted and addressed in the updated site grading plan.
| There are some areas where the curb heights are only 2cm. Please confirm. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted. As discussed with the Town reviewer, 5cm curb depressions are kept for vehicular travel, while for barrier-free pedestrian travel, the depressions are much less to not inhibit pedestrian travel (strollers, wheelchairs, etc.).
| There are existing streetlights along Harvest Moon Drive that are not shown on the engineering plans. One of these streetlights appears to be positioned within the proposed access. Please provide the necessary construction notes for the relocation of the streetlight and note that all related work is completed at the applicant’s expense. | Schaeffers | RTG |  |  | Servicing Plans by October 29, 2025 | This comment is noted. Existing streetlights are noted on SG-1. Refer to updated elctrical drawings for relocation.
| Swale slopes are to be a minimum of 1.5% as per Town standards. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted and addressed on drawing SG-1.
| Please provide the snow storage location. | Schaeffers | Q4 |  |  | Servicing Plans by October 29, 2025
| Show restoration notes for all proposed works within the Harvest Moon Drive ROW. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted. Please refer to drawing SG-1 for the driveway restoration, and drawing SEC-1 where the proposed storm sewer connection is noted to be backfilled with unshrinkable fill.
| SC-1 shows the outline of the underground parking space. Please confirm that the underground parking is not proposed for this development. | Schaeffers |  |  | no U/G parking | Servicing Plans by October 29, 2025 | This comment is noted refer to updated the SC-1 drawing which shows the outline of the proposed basement. No underground parking is proposed
| The Sediment Trap 1 is proposing to outlet to Emil Kolb Parkway. The Town defers to the Region to confirm if discharging to the Regional ROW is acceptable. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted.
| Include the standard drawings for TC-31R and TC-31L. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted. Refer to drawing SC-1 for an image of the signage.
| Remove the by-pass swale detail and fill and culvert detail (OPSD 221.040). | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted. Refer to updated SC-2 drawing.
Geotechnical and Hydrogeological Investigation
| Two Scoped Hydrogeological Assessments (SHAs) and one resilient letter was submitted in support of this application. According to the assessment submitted for 13688 Emil Kolb Parkway, dated May 2023, the proposed development on the site includes one underground parking level. Also Section 4.2.1 shows that a maximum dewatering requirement of 68,100 L/day which is above PTTW threshold. However, this is based on the superseded design which included for the multi-building underground parking structure.The PJR states that the current proposed development only consists of surface level parking with a partial underground storage area and the PTTW is no longer required. However no additional document has been provided to support this claim. The SHAs must be revised to match the latest site plan and information presented in the PJR. | HCS |  |  | HCS: Comment was provided in absence of the 2025 Construction Dewatering Assessment for the combined properties. DRAFT report was issued for internal review, FINAL report has not been issued yet. |  | This comment is noted. An updated Construction Dewatering Assement and Report has been provided with this submission for review.
| Please include a complete Water Balance calculation showing pre-development, unmitigated post-development and mitigated post-development infiltration volume analysis. | HCS |  |  | HCS: Likely a requirement now that the two properties have been combined. HCS can prepare a water balance assessment if required. |  | This comment is noted. An updated water balance table has been provided for review.
Noise Feasibility Study
| The Environmental Noise Assessment prepared by SLR dated February 27, 2025 has identified the road traffic noise on Emil Kolb Parkway and King Street as a potential noise source. Town Staff have reviewed the submitted noise report and have no concerns or comments. However, given Emil Kolb Parkway is a Regional road, the Noise Study shall be reviewed and approved by the Region of Peel in addition to Town Development Engineering. | [5 empty] | This comment is noted.
Environmental Site Assessment
| Town staff have reviewed the Phase One Environmental Site Assessments prepared by Pertitus and have no concerns with the submitted report. | noted |  |  |  |  | This comment is noted.
Photometrics Plan
| No photometric plan is included in this submission. Town Staff request the photometric plan to be included in the next submission to verify the illumination levels extending to the residential dwellings located to the west. | RTG |  |  |  | Draft Plan Provided | This comment is noted. An updated photmetrics plan as been provided.
Engineering Cost Estimate and Securities
| The engineering cost estimate, including retaining walls, was not included in the submission. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This condition is noted. A cost estimate has been included within this submission for Staff's review.
| Be advised that engineering securities will be required as part of site plan approvals. Town engineering securities will be based on 100% of the cost estimate for the internal site works. Final security amounts will be confirmed upon receipt of an acceptable engineering cost estimate. | noted |  |  |  |  | This condition is noted. Securities will be provided as required.
Town of Caledon Erosion and Sediment Control Notes
1 | All Erosion and Sediment Control (ESC) measures must be installed prior to the commencement of works on site and shall be maintained during all construction phases of the works. | Schaeffers |  |  |  |  | This comment is noted.
2 | The ESC strategies outlined on this plan are not static and may need to be upgraded/amended as site conditions change to prevent sediment release outside the work area. The Town is to be advised of any changes to ESC measures, and at the discretion of the Town, updated plans may be required. | Schaeffers |  |  |  |  | This comment is noted.
3 | The contractor is to assign an environmental monitor (EM) to assure construction activities comply with the environmental provisions and agency permits. The EM will be a qualified person as determined by the Town and/or Conservation Authority. The EM should submit inspection forms electronically to the Town and Conservation Authority upon request. | Schaeffers | Camcos |  | Environmental Monitor |  | This comment is noted.
4 | The contractor is responsible for maintaining all ESC measures in working condition at all times to the satisfaction of the Town and/or Conservation Authority. All damaged ESC measures should be repaired and/or replaced within 48 hours of the inspection. | Schaeffers | Camcos |  |  |  | This comment is noted.
5 | The contractor shall routinely inspect all ESC devices to ensure property working order. Frequency of inspections of ESC measures is as follows: | Schaeffers | Camcos |  |  |  | This comment is noted.
| During earthworks activities: | Schaeffers | Camcos |  |  |  | This comment is noted.
| On a weekly basis; | Schaeffers | Camcos |  |  |  | This comment is noted.
| Prior to predicted rainfall events; | Schaeffers | Camcos |  |  |  | This comment is noted.
| After every rainfall event; | Schaeffers | Camcos |  |  |  | This comment is noted.
| After significant snowmelt event; and | Schaeffers | Camcos |  |  |  | This comment is noted.
| Daily during extended rain or snowmelt periods. | Schaeffers | Camcos |  |  |  | This comment is noted.
| During times of no earthworks activity: | Schaeffers | Camcos |  |  |  | This comment is noted.
| Once every 2 weeks; | Schaeffers | Camcos |  |  |  | This comment is noted.
| After significant snowmelt events; | Schaeffers | Camcos |  |  |  | This comment is noted.
| After significant rainfall events (more than 25mm of rainfall in a 24 hour period). | Schaeffers | Camcos |  |  |  | This comment is noted.
6 | All construction vehicles must enter and exit the site only from the approved access route(s) as shown on the plans. Construction access will be maintained to the satisfaction of the Town/Region. Street sweeping is required as needed. | Camcos |  |  |  |  | This comment is noted.
7 | No construction activity or machinery shall be allowed beyond the silt fence or limits of the site works. | Camcos |  |  |  |  | This comment is noted.
8 | The contractor is responsible to implement dust control measures and construction best practice guidelines as approved by the Town and/or Conservation Authority. | Camcos |  |  |  |  | This comment is noted.
9 | All disturbed ground left inactive for 30 days shall be vegetated, subject to weather conditions. Disturbed areas are to be hydroseeded (or approved equivalent) to the satisfaction of the Town | Camcos |  |  |  |  | This comment is noted.
10 | All topsoil stockpiles shall be surrounded with sediment control fence. The maximum side slope shall be 2:1 (H:V). Once topsoil stripping is completed the stockpile shall be vegetated, subject to weather conditions, by hydroseeded, or an approved equivalent, to the satisfaction of the Town. | Camcos |  |  |  |  | This comment is noted.
11 | Contractor shall take care and control spills, fluids and materials during construction to minimize risk to the environment | Camcos |  |  |  |  | This comment is noted.
Town of Caledon General Notes – Site Plan Submissions
1 | The following standard notes are to appear on the Site Grading and Servicing Plans for site plan submissions: | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
2 | Construction for this project to comply with the most current version of the Development Standards, Policies and Guidelines, prepared by the Town of Caledon and the Ontario Provincial Standards and Specifications. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
3 | All construction shall be carried out in accordance with the requirements of the Occupational Health and Safety Act and Regulations for construction projects. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
| A minimum of forty-eight (48) hours prior to commencing construction within the municipal right of way the Contractor must contact the following: | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
| The Town of Caledon 905-584-2272 | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
| The Region of Peel, Hydro One, Rogers Cable, Enbridge Consumers Gas, Bell Canada, Fire and Emergency Services | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
4 | A Right of Way Occupancy permit must be obtained from the Town of Caledon a minimum 48 hours prior to commencing any works within the municipal road allowance. | Schaeffers |  |  | Right of Way Occupancy Permit | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
5 | All drainage to be self-contained and discharged to a location approved by the Town of Caledon and Conservation Authority prior to the issuance of a building permit. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
6 | Sediment control devices are to be installed prior to any construction on the site and shall be maintained throughout the construction period to the satisfaction of the Town and the applicable conservation authority. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
7 | Any changes to grades or servicing from the original approved site plan must be submitted by the Engineer to the Town for approval prior to construction. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
8 | A minimum of 1.5m clearance is to be provided from the limits of all sidewalks and driveways to existing utility structures within the municipal right of way. If this clearance is not maintained, they shall be relocated at the applicant’s expense. | Project Team |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
9 | Street curbs are to be continuous through the proposed entrance. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
10 | Municipal sidewalks shall be continuous through all entrances to the site and the curb shall be tapered back 600mm. Sidewalks shall be completely removed and replaced with a 200mm minimum concrete thickness, 32MPa and 5% to 7% air entrainment at all proposed industrial, commercial and institutional entrances. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
11 | All boulevards to be restored with 300mm minimum of topsoil and sod to the satisfaction of the Town. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
12 | The minimum pavement design for the asphalt driveway apron within the municipal road allowance shall be as follows: | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
| 40mm HL3 Asphalt | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
| 50mm HL8 Asphalt | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
| 150mm Granular ‘A’ | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
| 300mm Granular ‘B’ | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
| The consultant should review the above with respect to the expected usage. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
13 | Structural design of the fire route is required to support an 18 ton vehicle. | Q4 |  |  |  | 2025-10-29 | This comment is noted. As per comment #71 from the Region, internal roads must be designed to support a minimum of a 35 tonne fully-loaded waste collection vehicle. A note has been added to SPA003.
14 | Service Connection Backfill to be discussed with the Town. | Schaeffers |  |  |  | Servicing Plans by October 29, 2025 | This comment is noted, please refer to the General Notes Drawing.
Policy Planning
Dali Peng
1 | Please refer to landscape markups on the redline drawings and documents | Project Team |  |  |  |  | This comment is noted. The landscape drawings have been revised in accordance with the redlines.
2 | Please include the site plan application number (SPA 2021-0077) within the header of the Landscape Letter of Conformance and the Landscape Cost Estimate. | Landscape Planning |  |  |  | 2025-10-30 | This comment is notd. The site plan number has been included on the Cost Estimate
3 | Please include the site plan application number (SPA 2021-0077) on all landscape plan drawings. | Landscape Planning |  |  |  | 2025-10-30 | This comment is noted. The site plan number has been included on the landscape drawings
4 | Please update the arborist report to verify the health condition of Trees #414 and #427, as the provided photos do not clearly demonstrate that they are in poor condition. If they are healthy, tree compensation may be required. In addition, the arborist report indicates that four public trees are to be removed. A Cash-in-Lieu payment of $650 per tree will be required for their removal. | Landscape Planning |  |  |  | 2025-10-30 | This comment is noted.The condition of trees #414 and #427 have been verified as noted in the Arborist Report.
5 | Please provide a minimum of 3m wide planting strips along all proposed property lines and ensure no potentially invasive species are included in the proposed planting list. | Landscape Planning |  |  |  | 2025-10-30 | This comment is noted. No invasive species have been proposed in the planting list
6 | Please provide primary pedestrian access to ensure the safety of residents and avoid conflicts with traffic entering/exiting the site. The proposed walkway should be connected consistently. | Q4 | Landscape Planning |  |  |  | This comment is noted. A pedestrian walkway with line paint/stamped asphalt has been provided through the parking lot to connect the two buildings and provide better site circulation.Please refer to SPA001 and Landscape Drawings.
7 | Please explore the chance to arrange an outdoor playground on site plan. | Landscape Planning | Q4 |  |  |  | This comment is noted. An outdoor playground has been proposed as part of the future works and road widening. Please refer to the Landscape Drawings and SPA001.
8 | If a gateway entrance feature is required, its location should be illustrated on the landscape plans. | Landscape Planning |  |  |  | 2025-10-30 | This comment is noted. No entrance features are currently proposed. The building façade will include the street number and identifiers.
9 | Please indicate all snow storage areas with dash lines the landscape plan to ensure there are no conflicts with the planted areas. | Landscape Planning |  |  |  | 2025-10-30 | This comment is noted.Snow storage has been shown on the landscape drawings and kept clear of all shrub/tree planting.
10 | Please coordinate the proposed plantings with engineering drawings to demonstrate all utilities, and services (eg. fire hydrants, streetlights, telephone poles and pedestals, transformer vaults, guy wires, hydro poles and above-ground service boxes) with symbols and labelling, referring to General Notes-Landscaping on detail drawing D-1. | Landscape Planning | Schaeffers | RTG |  | 2025-10-30 | This comment is noted.Planting has been coordinated with the proposed servicing and symbols have been outlined on the drawings/details.
11 | Please include the Town’s standard detail drawing #709 for Sod installation in the landscape plan | Landscape Planning |  |  |  | 2025-10-30 | This comment is noted.
12 | Please relocate Concrete Sidewalk detail to engineering drawing set and included it in the engineering cost estimate. | Schaeffers | Landscape Planning |  |  | Servicing Plans by October 29, 2025 | This comment is noted.Concrete paving detail has been removed from the landscape drawing package and cost estimate and moved to the engineering drawings.
13 | Please revise and re-submit a cost estimate based on the red-line markups. The cost estimate needs to be originally stamped, signed and dated by an OALA licensed landscape architect. The amount of landscape securities the Town requires is based on 100% of the total cost of the landscape works. | Landscape Planning |  |  |  | 2025-10-30 | This comment is noted. An updated cost estimate has been provided in this submission
14 | As part of the next submission, please provide a letter from the landscape architect summarizing how each of the above items has been addressed. | Landscape Planning | Camcos |  |  | 2025-10-30 | This comment is noted. This matrix herein outlines how each item has been addressed.
15 | Please note that further revisions resulting from other departments or agencies comments may result in a further review and possible additional changes. Please note that review has been limited to the standards affected by the development proposed through this application only. | [5 empty] | This condition is noted.

## Region Comments
Official Plan Amendment, Zoning By-law Amendment, Site Plan Application and Draft Plan Condominium Application
POPA 2021-0011, RZ 2021-0015, SPA 2021-0077 and 21CDM 21004C
| Comment | Responsibility #1 | Responsibility #2 | Internal Due Date | Notes | Response
Development Services Engineering
| A functional Servicing Report dated February 2025 and prepared by Shaeffers Consulting Engineers was received. The report was sent to our program planning for review and modelling. Following the review, the FSR has been deemed satisfactory FSR and we have no further comments to offer. |  |  |  |  | This comment is noted.
Traffic Development
| A Traffic Impact Study (TIS) Addendum has been received by the Region as a part of the Second Submission, dated March 21, 2025. The Region offers no comments as there is no proposed access off of the Regional Road. |  |  |  |  | This comment is noted.
| The Region acknowledges that the applicant proposes access via Harvest Moon Drive and not Emil Kolb Parkway which the Region is in support of. |  |  |  |  | This comment is noted.
Waste Development
| A revised Waste Management Plan will be required to demonstrate the comments below: | Q4 |  |  |  | This comment is noted.
| Please also note that the waste-collection-design-standards-manual.pdf (peelregion.ca) requires that all dwelling units within a development must receive the same method of waste collection. For this development, it would be classified under sections 2 and 4 of the waste-collection-design-standards-manual.pdf (peelregion.ca) which is front-end collection. The Region recommends upsizing the waste bins to two compacted 4-yard bins for the entire development. | Q4 |  | 2025-10-27
Regional Waste Development staff would welcome a discussion with the applicant should clarification to any of the above comments be required or feedback be requested for any revised waste collection design.
Comments and Requirements to Inform the Site Plan Application Stage: | Comments and Requirements to Inform the Site Plan Application Stage:
The following requirements shall be completed by the applicant to the satisfaction of the Region prior to Site Plan approval:
Development Services Planning
| The Region may enter into a site plan agreement with the applicant, in which a $2,311.38 site plan agreement fee is required. Upon further review of the site plan application, it will be determined if the Region will require to enter into a site plan agreement. | Camcos |  |  |  | This comment is noted. Required fees will be paid.
Development Services Engineering
| Water and Sanitary Sewer Servicing of this site may require municipal and/or private easements and the construction, extension, twinning and/or upgrading of municipal services. All works associated with the servicing of this site will be at the applicant’s expense. The applicant will also be responsible for the payment of applicable fees, DC charges, legal costs and all other costs associated with the development of this site. | Camcos |  |  |  | This comment is noted.
| An existing 300 mm diameter water main is located on Emil Kolb Parkway & Harvest Moon Drive. | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
| Due to the size and function of the 1050mm diameter watermain on Emil Kolb Parkway, connection will not be permitted. | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
| An existing 375 mm diameter sanitary main is located on Emil Kolb Parkway & Harvest Moon Drive. | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
| This development proposal requires a water system looped to municipal water, to provide a redundant water supply, as per standard drawing 1-8-2. | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
| Please review the Region’s Water Design Criteria found at the following link: https://www.peelregion.ca/public-works/design-standards/pdf/water-design.pdf | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
| Please review the Region’s Sanitary Sewer Design Criteria found at the following link: https://www.peelregion.ca/public-works/design-standards/pdf/sanitary-sewerdesign- criteria.pdf | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
| The Region of Peel has an Environmental Compliance Approval (9582-B9TRLW) for the Regional Municipality of Peel Stormwater Management System. | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
| Therefore, it is the Region’s mandate that no additional flows are permitted, and no new connections are made to Regional Roads. | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
| Development flows are to be directed to the Local Municipality’s storm sewer system or watercourses, to the satisfaction of the Region of Peel, the local Conservation Authority and all concerned departments and agencies. Alternatively, flows can be mitigated using Low Impact Development Technologies. Developers are required to demonstrate how this will be achieved through a Stormwater Management Report. | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted. Please refer to the updated FSSR.
| Grading and Drainage approval by the Region of Peel is required prior to Site Plan Approval. | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
| No Grading will be permitted with any Region of Peel Right-of-Way to support adjacent developments. | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
| All resubmitted drawings including the Site Plan, Servicing and Grading drawings shall reflect the Region’s and Local Municipality’s road widening requirements | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
| A copy of the draft reference plan satisfactory to regional Traffic and Legal divisions will be required prior to site plan approval | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
Traffic Development
| All works within the Region's right-of-way will require a permit prior to any construction taking place. | Schaeffers | Camcos |  |  | This comment is noted.
Capital Project
| There is an on-going capital project #24-4825 taking place which includes the implementation of a round-about at the intersection of Emil Kolb Parkway and Harvest Moon Drive for which the Project Manager is Shahid Quraishi (shahid.quraishi@peelregion.ca) and can be consulted regarding the property impacts to the subject lands that are to be incorporated into the revised drawings. | Schaeffers | Camcos |  |  | This comment is noted.
| At this time, Peel Region does not have a detailed design consultant on board to perform the detailed design of the 24-4825 Coleraine Drive Grade Separation capital project. For that reason, the latest preliminary design drawings and reports the Region can refer you would be the capital project’s ESR and appendices available in the following link: https://peelregion.ca/construction/environmentalassessments/ coleraine-drive-grade-separation. | Schaeffers | Camcos |  |  | This comment is noted.
| Additional property requirements may be required to facilitate the Capital Project, this will be confirmed once a detailed design consultant is retained. | Schaeffers | Camcos |  |  | This comment is noted.
Property Dedication
| The Region requests the gratuitous dedication of lands to meet the Regional Official Plan requirement for Regional Road 150 (Emil Kolb Parkway/Coleraine Drive) which has a right of way of 50.5 metres, 25.25 metres from the centreline of the road allowance, within 245 metres of an intersection to protect for the provision of but not limited to: utilities, sidewalks, multiuse pathways and transit bay/shelters; | Camcos | Foglers |  |  | This comment is noted.
| The Region will require the gratuitous dedication of a 0.3 metre reserve along the frontage Regional Road 150 (Emil Kolb Parkway) behind the property line and daylight triangle, except at any approved access point; | Camcos | Foglers |  |  | This comment is noted.
| 15 x 15 metre daylight triangle at the intersection of Emil Kolb Parkway and Harvest Moon Drive/King Street; | Camcos | Foglers |  |  | This comment is noted. Patrick Amaral confirmed the Region will not require a 15 x 15 day light triangle in the case of a Roundabout condition (via email to Camcos on 2025-09-19).
| The applicant is required to gratuitously dedicate these lands to the Region, free and clear of all encumbrances. All costs associated with the transfer are the responsibility of the applicant. The applicant must provide the Region with the necessary title documents and reference plan(s) to confirm the Regions right-of-way; | Camcos | Foglers |  |  | This comment is noted.
Draft R-Plan
| A draft reference plan will be required for our review and approval prior to the plans being deposited. All costs associated with preparation of plans and the transfer of the lands will be solely at the expense of the applicant. Please be advised that the submitted draft reference plan needs to denote the centerline of the original road allowance and a dimension line from it to the proposed property line to demonstrate the adequate land dedication is being shown. | R-PE |  |  |  | This comment is noted. A draft reference plan will be provided subsequently.
| All comments provided should be reflected on the plan, including: | R-PE
| Please show a measurement/dimension from the centerline of road allowance to the new proposed property line to ensure proper land dedication has been depicted. | R-PE
| Please dimension the daylight triangle to ensure that the daylight triangle is 15m x 15m. | R-PE |  |  |  | No required as per Patrick Amaral. See response in Row 43.
Encroachments
| Landscaping, signs, fences, gateway features or any other encroachments are not permitted within the Region’s easements and/or Right of Way limits. | Landscape Planning |  |  |  | This comment is noted.
| Cranes will not be permitted to swing over a Regional Road unless a crane swing licence has been granted. | Camcos |  |  | DO WE NEED CRANE SWING. PROCESS ON CRANE SWING PERMIT TBD | This comment is noted.
Site Access
| The application proposes access via Harvest Moon Drive and not Emil Kolb Parkway which the Region is in support of. |  |  |  |  | This comment is noted.
Storm Water Management
| Provide a signed letter from the property owner committing to the operations and maintenance recommendations for the storm sewer system. | Camcos | Schaeffers |  | TO BE COMPLETE
Public Health
| Please consider for the future Site Plan is to include onsite outdoor amenity area for gathering and social connection. | Landscape Planning | Camcos |  |  | This comment is noted.
Hydrogeological Review
| The consultant has provided a summary of the review of the MECP WWRs database with a total of 20 wells identified within the 500 meters area: 1 not in use, 3 partial or no data, 5 abandoned wells, 8 test holes or monitoring wells, and 3 domestic wells | HCS |  |  |  | This comment is noted.
| A door-to-door survey was done in May 23 2023 with 7 houses canvased and zero response to the survey. | HCS |  |  |  | This comment is noted.
| Below grade designs were not available and therefore short term dewatering estimates did not include a Dewatering Design Elevation. Short (and long term if applicable) dewatering volume and zone of influence estimates should be refined when below grade designs are available. | HCS |  |  | Draft report provided. Final report pending updated site plan. | This condition is noted. Dewatering calucaltions and plans will be prepared once below grade detailed design is complete.
| The report Scoped Hydrogeological Assessment dated 2023-05-30 from the consultant provides complete information for the development application. Monitoring background information is provided and the MECP WWRs information is also accurate. However, the report is required to be revised to include the following through the Site Plan process: | HCS |  |  | Draft report provided. Final report pending updated site plan.
| Well Interference Contingency Plan | HCS |  |  | Draft report provided. Final report pending updated site plan.
| Refinement of short and long term dewatering / depressurization volume and zone of influence calculations | HCS |  |  | Draft report provided. Final report pending updated site plan.
| Discharge Management Plan including obtaining permit for municipal infrastructure if selected as discharge option | HCS |  |  | Draft report provided. Final report pending updated site plan.
Waste Management
| The applicants Fire and Garbage Collection Route is missing the following requirements, which must be verified and labelled on the drawings as per the wastecollection- design-standards-manual.pdf (peelregion.ca) (WCDSM). These requirements outlined below must be addressed in subsequent submissions prior to Site Plan approval: | Q4 |  | 2025-10-27 |  | This comment is noted. Please refer to SPA003 forupdates.
Overhead Clearance
| Outside the Collection Point: A clear height of 4.4 meters is required from the top of the access road, along the Waste Collection Vehicle access and egress route. This clearance must be free of obstructions such as sprinkler systems, ducts, wires, trees, or balconies. | Q4 |  | 2025-10-27 |  | This comment is noted and addressed.
Internal Roadways
| Internal roadways must be constructed of a hard surface material, such as asphalt or concrete, and designed to support a minimum of 35 tonnes, the weight of a fully loaded waste collection vehicle. | Nextrans |  | 2025-10-10 |  | This comment is noted.
Supported Structures:
| If the waste collection vehicle needs to drive onto or over a supported structure (e.g., air grate, transformer cover or underground parking garage), a letter from a Professional Engineer (licensed in Ontario) certifying the structure's capacity to support a 35-tonne vehicle must be provided to the Region. | Q4 |  | 2025-10-29 |  | This comment is noted. The development does not have an underground parking garage. A note has been added for road construction to meet this requirement.
| All bins of a single stream, whichever is larger, must be shown in the collection point area. The collection point area must also have a 10-square-meter area for the set-out of bulky waste items. | Q4 |  | 2025-10-29 |  | This comment is noted. Please refer to SPA003 for updates.
| The collection point area must have a minimum overhead clearance of 7.5 meters. | Q4 |  | 2025-10-29 |  | This comment is noted. Please refer to SPA003 for updates.
| A Collection Point: solid level (+/- 2%) concrete pad is required. The concrete pad dimensions must be provided and must extend a minimum of 1.5 meters in length outside the opening of the concealed waste collection point to accommodate the front wheels of the waste collection vehicle. See Appendix 4.0 of the WCDSM for an illustration of the requirements. | Q4 |  | 2025-10-29 |  | This comment is noted. Please refer to SPA003 for updates.
| At the site plan stage, the developer must also illustrate on the Waste Management Plan that the front-end bins of the larger stream can be placed in the correct position for servicing without the need for jockeying by property management on collection days. (The developer can refer to Appendix 4 of the WCDSM available at wastecollection- design-standards-manual.pdf (peelregion.ca) for proper bin positioning without jockeying). | Q4 |  | 2025-10-29 |  | This condition is noted. Jockeying for collection purposes will be required, as the bins will be stored in a designated room on the ground floor of the midrise building.
Jockeying of Bins
| However, if all reasonable attempts have been undertaken and these requirements stated in Appendix 4 cannot be met, reliance on property management staff to facilitate waste collection will be considered at the Region's discretion subject to the following requirements: | Q4 |  | 2025-10-29 |  | This comment is noted.
1 | The bins should be properly positioned in the collection area on the day of collection before 7 am. | Q4 |  | 2025-10-29 |  | This comment is noted.
2 | The driver is not required to exit the collection vehicle to facilitate collection. | Maple Ridge |  |  |  | This comment is noted.
3 | Property management is responsible for moving bins during collection. | Maple Ridge |  |  |  | This comment is noted.
4 | The Region will not be responsible for emptying bins that are inaccessible to the collection vehicle. | Maple Ridge |  |  |  | This comment is noted.
5 | Property management must be visible to waste collection vehicle on approach to site, otherwise the waste collection vehicle will not enter the site. | Maple Ridge |  |  |  | This comment is noted.
6 | Property management will be responsible for safely maneuvering waste collection vehicles into and/or out of, as well as around the site. | Maple Ridge |  |  |  | This comment is noted.
7 | Property management staff will be responsible for moving bins to the staging area at the time of collection and returning to storage room following collection. | Maple Ridge |  |  |  | This comment is noted.
| If the development will require jockeying of the bins by property management, please provide the following jockeying notes 1 to 7 stated above on the Waste Management Plan. | Q4 |  | 2025-10-29 |  | This comment is noted. Please refer to SPA003 for updates.
| For additional details regarding the requirements outlined above and in the Region of Peel Waste Collection Design Standards Manual, please refer to the Region of Peel Waste Collection Design Standards Manual, which can be accessed at: wastecollection- design-standards-manual.pdf (peelregion.ca) | Q4 |  | 2025-10-29
| Regional Waste Development staff would welcome a discussion with the applicant should clarification to any of the above comments be required or feedback be requested for any revised waste collection point location. |  |  |  |  | This comment is noted.
Additional Notes
Development Services Engineering
| A satisfactory Servicing submission and 1st Submission fee as per the latest fee by-law is required prior to the Site Plan application being approved; | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
| A satisfactory Servicing submission is required prior to clearance for site plan approval; | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
| Final Regional Site Servicing connection approvals are required prior to the local municipality issuing Building Permit | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted.
| Fire Protection approval from the local municipality is required prior to Region of Peel Site Servicing connection approval | Camcos |  | Servicing Plans by October 29, 2025 |  | This comment is noted. Approval will be obtained prioir to servicing approval.
| Please indicate if the proposal will be pursuing LEED certification. | Camcos | Q4 | 2025-10-29 |  | This comment is noted. No LEED certification has been obtained.
| Please be advised that due to the ongoing developments of the novel coronavirus outbreak, the Region of Peel is currently implementing various measures to ensure the safety of our customers, employees and the workplace. Our front counter is now closed to the public and our staff have been directed to work from home for the foreseeable future. Therefore, Servicing Connections cannot process any payments over the counter at this time, however, we will accept Electronic Fund Transfers (EFT). | Camcos |  |  |  | This comment is noted.
| Please contact Servicing Connection at siteplanservicing@peelregion.ca for the process to submit an Electronic Fund Transfer for your servicing application fees. | Camcos |  |  |  | This comment is noted.
| All our design criteria, standards, specifications, procedures and report and submission requirements are found on-line at https://www.peelregion.ca/publicworks/ design-standards/#procedures | Schaeffers |  |  |  | This comment is noted.
| Please refer and adhere to the Regional by-laws that are applicable to your proposal, such as but not limited to the Water, Wastewater and Backflow Prevention by-laws https://www.peelregion.ca/council/bylaws/archive.asp | Schaeffers |  |  |  | This comment is noted.
| Please refer to the Latest Fees Bylaw. All fees may be subject to change on annual basis pending Council approval. | Camcos |  |  |  | This comment is noted.
| Please refer to our Standard Drawings on-line to determine which standards are applicable to your project. The most current standard drawings are found on-line at https://www.peelregion.ca/public-works/design-standards/#drawings | Schaeffers |  |  |  | This comment is noted.
| For location of existing water and sanitary sewer Infrastructure please contact Records at 905-791-7800 extension 7882 or by e-mail at PWServiceRequests@peelregion.ca | Schaeffers |  |  |  | This comment is noted.
| Please refer to Section 3 of our Site Plan Process for Site Servicing Submission Requirements found on-line at https://www.peelregion.ca/public-works/designstandards/ pdf/site-plan-process2009.pdf | Schaeffers |  |  |  | This comment is noted.
| If you have questions regarding the Site Servicing Application Submission Requirements, please contact Site Plan Servicing at 905-791-7800 extension 7973 or email siteplanservicing@peelregion.ca | Schaeffers |  |  |  | This comment is noted.
| Servicing for the proposed development must comply with the Local Municipality’s Requirements for the Ontario Building Code and most current Region of Peel standards | Schaeffers |  |  |  | This comment is noted.
Servicing Connections Payment Process
| Please be advised that the approved updated 2024 Fees by-law includes increases in some Engineering Fees. All fees are subject to change on annual basis pending Council approval. Securities will be 100% of the cost estimate which will provided by the applicant once the servicing design is satisfactory. Servicing connections will provide instructions regarding what should be included in the cost estimate. It will include work subject to Region of Peel approval within the road allowance and at the property line (water valve and chamber and sanitary/storm sewer maintenance hole). Servicing Connections is accepting payments by Electronic Fund Transfers (EFT) and will accept a Letter of Credit as an alternative for collecting securities. Please complete the table below with your information and provide the completed table to Finance at eftadvice@peelregion.ca for payment processing (all fields are mandatory). We will not be able to accept or process the payment without the completed table. Once the Servicing Connections receives confirmation that the funds have been successfully transferred to the Region of Peel, a receipt will be issued to the payer via email. | Camcos |  |  |  | This condition is noted.
Traffic Development
| A detailed engineering submission of road and access works will be required for our review and comment, designed, stamped and signed by a Licensed Ontario Professional Engineer. The engineering submission must include the removals, new construction and grading, typical sections and pavement markings and signing drawings. All works within Region of Peel’s right of way must be designed in accordance with the Public Works, “Design Criteria and Development Procedures Manual” and “Material Specifications and Standard Drawings Manual”; | Schaeffers | Nextrans | Servicing Plans by October 29, 2025 |  | This comment is noted. An engineering submission will not be required as the works within Emil Kolb are a capital works project proposed by the Region of Peel.
| The Owner shall submit to the Region a detailed cost estimate, stamped and signed by a Licensed Ontario Professional Engineer, of the proposed road and access works within the Regional right of way; | Schaeffers |  | Servicing Plans by October 29, 2025 |  | This comment is noted. A cost estimate will be required subsequently upon agreement of grading and servicing strategy.
| Securities shall be submitted in the form of either a letter of credit or certified cheque, in the amount of 100% of the approved estimated cost of road and access works along Regional Road 150 (Emil Kolb Parkway); | Camcos |  |  |  | This comment is noted.
| A 10.8% engineering and inspection fee shall be paid to the Region based on the approved estimated cost of road and access works (minimum $1,724.41); | Camcos |  |  |  | This comment is noted. All engineering and inspection fees will be paid.
| The Owner will be required to submit the following prior to commencement of works within the Region’s right-of-way: | Schaeffers | Camcos | Servicing Plans by October 29, 2025 |  | This comment is noted.
| Completed Road Occupancy Permit and fee, as per the Region’s User Fees and Charges By-law; | Schaeffers | Camcos | Servicing Plans by October 29, 2025 | Road Occupancy Permit to be Applied for. | This comment is noted.
| Completed Notice to Commence Work; | Schaeffers | Camcos | Servicing Plans by October 29, 2025 |  | This comment is noted.
| Provide proof of insurance with the Region of Peel added to the Certificate of Insurance as an additional insured with $5 million minimum from the Contractor; | Camcos | Camcos | Servicing Plans by October 29, 2025 |  | This comment is noted.
| Please note that any proposed construction within the Region of Peel’s right of way is pending PUCC approval (minimum six week process). Please note that PUCC circulation requirements have recently changed. We require PDF version of the full drawing set it is to be sent via email, and cannot exceed 10MB per email. | Schaeffers | Camcos | Servicing Plans by October 29, 2025 |  | This comment is noted.
| Please be advised that any concerns or issues identified by the utility company will be the responsibility of the Owner/Applicant to address and resolve directly with the utility company. | Schaeffers | Camcos | Servicing Plans by October 29, 2025 |  | This comment is noted.
| All costs associated with the design and construction of road and access works will be 100% paid by the Owner. | Camcos |  |  |  | This comment is noted.
Comments to Inform the Draft Plan of Condominium Application Stage
| Through the Draft Plan of Condominium application, the region will require a copy of the declaration and description with a completed scheduled A for review and a satisfactory condominium plan prior to registration of the condominium. Additional comments may apply following further review of the application. | Camcos | Foglers |  | Declaration and Description of Condo | This comment is noted. The declaration and description will be provided subsequently.

## External Comments
| Comment | Responsibility #1 | Responsibility #2 | Notes | Response
Bell Canada
Mohammad Bangee
mohammad.bangee@bell.ca
circulations@bell.ca
1) | The Owner acknowledges and agrees to convey any easement(s) as deemed necessaryby Bell Canada to service this new development. The Owner further agrees andacknowledges to convey such easements at no cost to Bell Canada. | Camcos | Foglers |  | The provided comments are noted.
2) | The Owner agrees that should any conflict arise with existing Bell Canada facilitieswhere a current and valid easement exists within the subject area, the Owner shall beresponsible for the relocation of any such facilities or easements at their own cost. Upon receipt of this comment letter, the Owner is to provide Bell Canada with servicingplans/CUP at their earliest convenience to planninganddevelopment@bell.ca to confirmthe provision of communication/telecommunication infrastructure needed to service thedevelopment. | Camcos
| The Owner acknowledges and agrees that it is the responsibility of the Owner to provide entrance/service duct(s) at their own cost from Bell Canada’s existing network infrastructure to service this development. In the event that no such network infrastructure exists, in accordance with the Bell Canada Act, the Owner shall be required to pay for the extension of such network infrastructure. | Camcos
| If the Owner elects not to pay for the above noted connection, Bell Canada may decide not to provide service to this development. | Camcos
Dufferin - Peel Catholic District School Board
Krystina Koops
krystina.koops@dpcdsb.org
| That the applicant shall agree to include the following warning clauses in all offers of purchase and sale of residential lots. |  |  |  | This comment is noted. Warning clauses will be inserted into the Agreement of Purchase of Sale for all lots.
a) | "Whereas, despite the best efforts of the Dufferin-Peel Catholic District School Board, sufficient accommodation may not be available for all anticipated students from the area, you are hereby notified that students may be accommodated in temporary facilities and/or bussed to a school outside of the neighbourhood, and further, that students may later be transferred to the neighbourhood school." | Camcos | Foglers
b) | "That the purchasers agree that for the purpose of transportation to school, the residents of the subdivision shall agree that children will meet the bus on roads presently in existence or at another place designated by the Board." | Camcos | Foglers
Enbridge
Willie Cornelio
| Enbridge Gas does not object to the proposed application(s) however, we reserve the right to amend or remove development conditions. This response does not signify an approval for the site/development. | Camcos |  |  | The provided comments are noted.
| Please always call before you dig, see web link for additional details: https://www.enbridgegas.com/-/media/Extranet-Pages/Safety/Dig-safety-forcontractors/faqs.pdf?rev=3d3a2ccd7027463c89a953133aadc4e4 | Camcos
| This response does not constitute a pipe locate, clearance for construction or availability of gas. | Camcos
| The applicant shall use the Enbridge Gas Get Connected tool to determine gas availability, service and meter installation details and to ensure all gas piping is installed prior to the commencement of site landscaping and/or asphalt paving. (https://enbridge.outsystemsenterprise.com/GetConnected_Th/Login2?OriginalURL=https%3A%2F%2Fenbridge.outsystemsenterprise.com%2FGetConnectedApp_UI%2F) | Camcos
| If the gas main(s) needs to be relocated as a result of changes in the alignment or grade of the future road allowances or for temporary gas pipe installations pertaining to phased construction, all costs are the responsibility of the applicant. | Camcos
| In the event that easement(s) are required to service this development, and any future adjacent developments, the applicant will provide the easement(s) to Enbridge Gas at no cost. | Camcos
TRCA
Andrea Terella
andrea.terella@trca.ca
| Please be advised that the subject properties as part of the above noted applications are not located within TRCA’s Regulated Area. As such, any site alteration or development on the property would not require a permit from TRCA. Further the overall size of the properties is small under 1ha. Based on the comments noted above, TRCA defers Stormwater Management review to the Town. | Noted |  |  | This comment is noted.